## Slide 1: Project Name: FIS Workspace
Prepared By: Akash Kumar
Date: 01st July’26

## Slide 2: Situation:
Before the COVID‑19 pandemic, Fidelity Information Services (FIS) India operated as a fully on‑site organization. Employees worked in multiple shifts to meet business needs, and the company maintained leased office space sized for about 4,000 on‑site employees.
When the pandemic began, FIS shifted rapidly to work from home, halting normal in‑office operations. The sudden change created cash‑flow and working‑capital pressures across many organizations, including FIS, forcing a re‑evaluation of real‑estate and operating costs.
To reduce costs and streamline operations, FIS moved to a hybrid working model nationwide. The company released leased workspace back to building owners and began outsourcing parts of its operations — moving some functions to Genpact and voice processes to Teleperformance. These changes reduced the number of employees who need permanent seats at FIS offices.
After vaccinations rolled out, FIS set a new target for in‑office capacity: no more than 700 seats. The goal is to maintain a lean physical footprint to cut lease and operating expenses while supporting hybrid work and outsourced operations.

## Slide 3: Problem:
There are many problems. Some of the problems are listed below:
Overcapacity and Excess Real‑Estate
  FIS needs some extra seat for conducting the townhalls with leadership team
  Lease contracts and exit windows misaligned with consolidation timeline.
Operational and move management problems
  Complex moves across floors/buildings with many assets and teams.
  Occasional high‑demand days could exceed the reduced seating capacity.
Inaccurate Space and Asset Inventory
  Complex moves across floors/buildings with many assets and teams.
  Local labor, safety, or data‑protection rules may be overlooked during consolidation.
  Townhall and Event Seating Needs
  The office must retain flexible seating or a reserve area to host leadership townhalls and large gatherings.

## Slide 4: Opportunity:
There are following opportunities which is identified after Covid-19. Some of the opportunities are listed below:
Flexible Lease Strategies — Organization needs shorter terms Lease so that it can break easily. Also, it should be break clauses, and sublease options to increase agility and reduce exit costs.
Workspace-as-a-Service Options — Use coworking or managed space providers for overflow and project teams to avoid long‑term commitments.
Event and Collaboration Hubs — Convert surplus space into Innovation Labs, Training Center, or Client Briefing Suites that add business value.
Sustainability and Energy Savings — Right‑size utilities, implement zoned HVAC, and report carbon reductions as part of ESG goals.
Advanced Utilization Analytics — Apply predictive analytics to forecast demand, optimize desk ratios, and plan seasonal capacity.
Efficient Seat Booking — Seat Booking can be easily done within 30 seconds.

## Slide 5: Goals:
As an Organization, FIS is trying to build an app for all the employees so that they can book their seat/workspace for the day, week or the month.
The Primary Objectives/Aims/Goals of seat booking application are as follows:
Reduction in leased square feet validated by 3‑month utilization data.
Eliminate manual seat booking by automatic booking done via SSO login (fis username and password).
Enable flexible reservations for desks, collaboration spaces, and townhall seating (day/week/month).
Reduced time for seat confirmation/parking space confirmation. Also, ensure no seat booking request missed by seat booking application.
Provide real‑time dashboards for facilities and leadership showing utilization, no‑show rates, and peak demand.

## Slide 6: Project Objectives:
Build a user‑friendly web and mobile application that enables FIS employees to reserve desks, meeting rooms, and event seating for a day, week, or month, and delivers verified occupancy data to support workspace right‑sizing.
Space Optimization
  Reduce FIS’s physical footprint to support a validated approx. 700 in‑office seats target.
Booking and Occupancy Verification
  Deliver a mobile and web booking app that allows employees to reserve desks, meeting rooms, and event seating for day / week / month and supports mandatory check‑in.
Seat book- anytime/anywhere
  Employee can book a seat as per their choice.
Role‑based Controls and Approvals
  Implement manager approval flows, team quotas, and admin overrides.
Ensure Data Accuracy
  Minimize typographical and manual errors by integrating online seat booking application.

## Slide 7: Success Criteria:
Deliver a production‑ready web and mobile seat‑booking application that is stable, performant, and accepted by users.
Acceptance: MVP deployed to pilot site; production rollout plan approved.
Active adoption:
  Adopted by > 70% employees of pilot project.
  Workspace seat booking interface improved by at least 50% in post‑pilot survey.
  Booking completed within 60 seconds
Occupancy, Booking and Analytics
  Check‑in compliance: Booking vs check‑in more than 80% by Employees.
  No‑show control: No‑show rate ≤20% after enforcement of check‑in rules.
  Utilization reporting: Daily occupancy, peak utilization, and no‑show reports available and accurate within 24 hours.
System Uptime and Availability
  The automated platform maintains at least 99% availability to keep services running without interruption.

## Slide 8: Method/Approach:
For Building this application, we will use consider hybrid approach. All the Documentation work will be done in Waterfall model as it is sequential model. Application Development phase will be completed in Agile model.
1. Requirement Gathering:
Firstly need to understand the Business Requirement to identify the exact need of the. Try to explore different seat booking applications i.e. BookmyShow.com, Bus Seat Booking Application, Train Boking Application, etc. Apply Questionnaire, Brainstorming
Prepare document for Business Requirements, Functional/Non-Functional Requirements.
2. System Designing:
Create system Flow/design along with Use Cases, Flow Chart and Prototyping
Also, Prepare Database schema/Architecture and Network Architecture
3. Development:
Follow Agile Model for developing application. Follow the following modules
  User Registration, User Login via SSO login
  Select Building floor plan, select seats and select Date/Date-Range and Confirm the seat.
  User and Reporting manager will receive booking confirmation.
4. Testing: Conduct the UAT for Booking tickets, same seat booking done by 2 employees, etc. UAT done on UAT server.
5. Deployment: After UAT, Deploy the application will deploy to Production Server.
6. Maintenance and Support: Provide post-deployment support for bug files, performance increased and enhancements.

## Slide 9: Resources:
Human/People Resources:
Project Manager (1) —Responsible look for Project Delivery and see overall delivery, client coordination, schedule and collaboration with each team. Responsible for defininig priorities, acceptance of features
Business Analyst (1) —Requirement Gathering, Documentation, Support in UAT/Go Live environment and in maintenance.
Database Admin (1) — Design Database Schema and manage to store information related to workspace seats.
Developers (5) — APIs, booking logic, integrations, Web/Mobile UI, Desk/Room/Floor Maps
Testers (1–2) — Prepare detailed testing plan i.e. UNIT Testing, Integration Testing, System Testing & UAT.
Timeline:
Estimated Timeline for Project Delivery: 4-5 Months.
Requirement Gathering and Analysis- 1 Month
System Design – 1 Month
Development & Testing- 3 Month
Budget: Estimated Budget 60 Lakh INR
Other Resources:
Hardware: Dedicated servers for hosting the application and database. Also, focus on Backup and Business Continuity Plan.
Software: Development tools (Database Tools, Java IDEs), Automated E-mail parsing tools,
Network: High- speed internet connection, VPN or secure email gateway for

## Slide 10: Risk:
Technical Risks
  System downtime or performance issues (failure to meet 99% uptime target).
  Bugs in booking logic (e.g., double‑booking seats, failed check‑ins).
  Integration challenges with SSO login and internal systems.
Operational Risks
  Inaccurate seat/asset inventory leading to wrong bookings.
  Employees not adopting the app (less than 70% usage in pilot).
  High no‑show rates despite check‑in enforcement.
Compliance & Security Risks
  Non‑compliance with local labor, safety, or data‑protection rules.
  Unauthorized access if role‑based controls fail.
Change Management Risks
  Lack of training/support leading to poor adoption.
  Leadership townhalls/events exceeding reduced seating capacity.
Financial Risks
  Budget overruns beyond the estimated ₹60 lakh.
  Delays in project delivery (timeline 4–5 months slipping).

## Slide 11: Dependencies:
Dependencies are the pre‑conditions your project needs — if any of them fail or are delayed, the project timeline and success criteria will be impacted.
Technology Dependencies
Stable SSO login integration with FIS systems.
Availability of servers, VPN, and secure network setup.
Data Dependencies
Accurate seat and asset inventory data before booking logic works.
Updated floor maps and seating layouts.
Real‑time occupancy data feeds for dashboards.
Process Dependencies
Lease exit timelines aligned with workspace consolidation.
UAT completion before production deployment.
Resource Dependencies
Availability of developers, testers, and DB admin as per project schedule.
Timely input from Business Analyst for requirement gathering.
Budget release (₹60 lakh) and procurement of hardware/software tools.
Compliance Dependencies
Adherence to local labor, safety, and data‑protection rules.
Approval from leadership for townhall/event seating arrangements.

## Slide 12: THANK YOU!